## Summary
HOMELAND GROUP ¦ STAIRCASE RAILING STATUS REPORT ¦ Granite Fixing & MS Railing Installation
Report Date: 30 May 2026 ¦ Data fetched live from Google Sheets on 30 May 2026
Tower | Granite Done | Granite Pending | Granite Total | Granite % | MS Railing Done | MS Railing Pending | MS Railing Total | MS Railing %
Tower 1 | 8 | 34 | 42 | 19% | 0 | 35 | 35 | 0%
Tower 2 | 30 | 12 | 42 | 71% | 0 | 33 | 33 | 0%
Tower 3 | 48 | 2 | 50 | 96% | 44 | 1 | 45 | 98%
Tower 4 | 48 | 2 | 50 | 96% | 43 | 7 | 50 | 86%
Tower 5 | 41 | 5 | 46 | 89% | 41 | 9 | 50 | 82%
ALL TOWERS | 175 | 55 | 230 | 76% | 128 | 85 | 213 | 60%

## Tower 1
Tower 1 ¦ Staircase Railing ¦ Granite Fixing & MS Railing Installation
Report Date: 30 May 2026 ¦ Source: Homeland ED Tracker – Google Sheets (Live)
Floor No. | Side / Flat | Granite Fixing (GRANITE FOR STAIRCASE RAILING) | MS Railing Installation | Remarks / Notes
1 Floor | RHS | ✓ Done | 📝 Railing Install After Granite
1 Floor | LHS | ✓ Done | -
2 Floor | RHS | ✓ Done | -
2 Floor | LHS | ✓ Done | -
3 Floor | RHS | ✓ Done | -
3 Floor | LHS | ✓ Done | -
4 Floor | RHS | ✓ Done | -
4 Floor | LHS | ✓ Done | -
5 Floor | RHS | ✗ Pending | -
5 Floor | LHS | ✗ Pending | -
6 Floor | RHS | ✗ Pending | ✗ Pending
6 Floor | LHS | ✗ Pending | ✗ Pending
7 Floor | RHS | ✗ Pending | ✗ Pending
7 Floor | LHS | ✗ Pending | ✗ Pending
8 Floor | RHS | ✗ Pending | ✗ Pending
8 Floor | LHS | ✗ Pending | ✗ Pending
9 Floor | RHS | ✗ Pending | ✗ Pending
9 Floor | LHS | ✗ Pending | ✗ Pending
10 Floor | RHS | ✗ Pending | ✗ Pending
10 Floor | LHS | ✗ Pending | ✗ Pending
11 Floor | RHS | ✗ Pending | ✗ Pending
11 Floor | LHS | ✗ Pending | ✗ Pending
12 Floor | RHS | ✗ Pending | ✗ Pending
12 Floor | LHS | ✗ Pending | ✗ Pending
13 Floor | RHS | ✗ Pending | ✗ Pending
13 Floor | LHS | ✗ Pending | ✗ Pending
14 Floor | RHS | ✗ Pending | ✗ Pending
14 Floor | LHS | ✗ Pending | ✗ Pending
15 Floor | RHS | ✗ Pending | ✗ Pending
15 Floor | LHS | ✗ Pending | ✗ Pending
16 Floor | RHS | ✗ Pending | ✗ Pending
16 Floor | LHS | ✗ Pending | ✗ Pending
17 Floor | RHS | ✗ Pending | ✗ Pending
17 Floor | LHS | ✗ Pending | ✗ Pending
18 Floor | RHS | ✗ Pending | ✗ Pending
18 Floor | LHS | ✗ Pending | ✗ Pending
19 Floor | RHS | ✗ Pending | ✗ Pending
19 Floor | LHS | ✗ Pending | ✗ Pending
20 Floor | RHS | ✗ Pending | ✗ Pending
20 Floor | LHS | ✗ Pending | ✗ Pending
21 Floor | RHS | ✗ Pending | ✗ Pending
21 Floor | LHS | ✗ Pending | ✗ Pending
22 Floor | RHS | - | ✗ Pending
22 Floor | LHS | - | ✗ Pending
COMPLETION SUMMARY |  | Granite Done: 8/42 = 19% | MS Railing Done: 0/35 = 0%
LEGEND: ✓ Done (Green) ✗ Pending (Red) 📅 Scheduled Date (Yellow) 📝 Remark/Note (Orange) – Not Entered (Grey)

## Tower 2
Tower 2 ¦ Staircase Railing ¦ Granite Fixing & MS Railing Installation
Report Date: 30 May 2026 ¦ Source: Homeland ED Tracker – Google Sheets (Live)
Floor No. | Side / Flat | Granite Fixing (GRANITE FOR STAIRCASE RAILING) | MS Railing Installation | Remarks / Notes
1 Floor | RHS | ✓ Done | 📝 plaster pending
1 Floor | LHS | ✓ Done | -
2 Floor | RHS | ✓ Done | -
2 Floor | LHS | ✓ Done | -
3 Floor | RHS | ✓ Done | -
3 Floor | LHS | ✓ Done | -
4 Floor | RHS | ✓ Done | -
4 Floor | LHS | ✓ Done | -
5 Floor | RHS | ✓ Done | -
5 Floor | LHS | ✓ Done | -
6 Floor | RHS | ✓ Done | ✗ Pending
6 Floor | LHS | ✓ Done | ✗ Pending
7 Floor | RHS | ✓ Done | ✗ Pending
7 Floor | LHS | ✓ Done | ✗ Pending
8 Floor | RHS | ✓ Done | ✗ Pending
8 Floor | LHS | ✓ Done | ✗ Pending
9 Floor | RHS | ✓ Done | ✗ Pending
9 Floor | LHS | ✓ Done | ✗ Pending
10 Floor | RHS | ✓ Done | ✗ Pending
10 Floor | LHS | ✓ Done | ✗ Pending
11 Floor | RHS | ✓ Done | ✗ Pending
11 Floor | LHS | ✓ Done | ✗ Pending
12 Floor | RHS | ✓ Done | ✗ Pending
12 Floor | LHS | ✓ Done | ✗ Pending
13 Floor | RHS | ✓ Done | ✗ Pending
13 Floor | LHS | ✓ Done | ✗ Pending
14 Floor | RHS | ✓ Done | ✗ Pending
14 Floor | LHS | ✓ Done | ✗ Pending
15 Floor | RHS | ✓ Done | ✗ Pending
15 Floor | LHS | ✓ Done | ✗ Pending
16 Floor | RHS | ✗ Pending | ✗ Pending
16 Floor | LHS | ✗ Pending | ✗ Pending
17 Floor | RHS | ✗ Pending | ✗ Pending
17 Floor | LHS | ✗ Pending | ✗ Pending
18 Floor | RHS | ✗ Pending | ✗ Pending
18 Floor | LHS | ✗ Pending | ✗ Pending
19 Floor | RHS | ✗ Pending | ✗ Pending
19 Floor | LHS | ✗ Pending | ✗ Pending
20 Floor | RHS | ✗ Pending | ✗ Pending
20 Floor | LHS | ✗ Pending | ✗ Pending
21 Floor | RHS | ✗ Pending | ✗ Pending
21 Floor | LHS | ✗ Pending | ✗ Pending
COMPLETION SUMMARY |  | Granite Done: 30/42 = 71% | MS Railing Done: 0/33 = 0%
LEGEND: ✓ Done (Green) ✗ Pending (Red) 📅 Scheduled Date (Yellow) 📝 Remark/Note (Orange) – Not Entered (Grey)

## Tower 3
Tower 3 ¦ Staircase Railing ¦ Granite Fixing & MS Railing Installation
Report Date: 30 May 2026 ¦ Source: Homeland ED Tracker – Google Sheets (Live)
Floor No. | Side / Flat | Granite Fixing (GRANITE FOR STAIRCASE RAILING) | MS Railing Installation | Remarks / Notes
BASEMENT -2 | LHS | ✓ Done | ✓ Done
BASEMENT -2 | RHS | ✓ Done | ✓ Done
BASEMENT -1 | LHS | ✓ Done | ✓ Done
BASEMENT -1 | RHS | ✓ Done | ✓ Done
1 Floor | LHS | ✓ Done | ✓ Done
1 Floor | RHS | ✓ Done | ✓ Done
2 Floor | LHS | ✓ Done | ✓ Done
2 Floor | RHS | ✓ Done | ✓ Done
3 Floor | LHS | ✓ Done | ✓ Done
3 Floor | RHS | ✓ Done | ✓ Done
4 Floor | LHS | ✓ Done | ✓ Done
4 Floor | RHS | ✓ Done | ✓ Done
5 Floor | LHS | ✓ Done | ✓ Done
5 Floor | RHS | ✓ Done | ✓ Done
6 Floor | LHS | ✓ Done | ✓ Done
6 Floor | RHS | ✓ Done | ✓ Done
7 Floor | LHS | ✓ Done | ✓ Done
7 Floor | RHS | ✓ Done | ✓ Done
8 Floor | LHS | ✓ Done | ✓ Done
8 Floor | RHS | ✓ Done | ✓ Done
9 Floor | LHS | ✓ Done | ✓ Done
9 Floor | RHS | ✓ Done | ✓ Done
10 Floor | LHS | ✓ Done | ✓ Done
10 Floor | RHS | ✓ Done | ✓ Done
11 Floor | LHS | ✓ Done | ✓ Done
11 Floor | RHS | ✓ Done | ✓ Done
12 Floor | LHS | ✓ Done | ✓ Done
12 Floor | RHS | ✓ Done | ✓ Done
13 Floor | LHS | ✓ Done | ✓ Done
13 Floor | RHS | ✓ Done | ✓ Done
14 Floor | LHS | ✓ Done | ✓ Done
14 Floor | RHS | ✓ Done | ✓ Done
15 Floor | LHS | ✓ Done | ✓ Done
15 Floor | RHS | ✓ Done | ✓ Done
16 Floor | LHS | ✓ Done | ✓ Done
16 Floor | RHS | ✓ Done | ✓ Done
17 Floor | LHS | ✓ Done | ✓ Done
17 Floor | RHS | ✓ Done | ✓ Done
18 Floor | LHS | ✓ Done | ✓ Done
18 Floor | RHS | ✓ Done | ✓ Done
19 Floor | LHS | ✓ Done | ✓ Done
19 Floor | RHS | ✓ Done | ✓ Done
20 Floor | LHS | ✓ Done | ✓ Done
20 Floor | RHS | ✓ Done | ✓ Done
21 Floor | LHS | ✓ Done | 📝 need granite
21 Floor | RHS | ✓ Done | -
21 Floor | LHS | ✓ Done | -
21 Floor | RHS | ✓ Done | -
22 Floor | LHS | ✗ Pending | -
22 Floor | RHS | ✗ Pending | -
COMPLETION SUMMARY |  | Granite Done: 48/50 = 96% | MS Railing Done: 44/45 = 98%
LEGEND: ✓ Done (Green) ✗ Pending (Red) 📅 Scheduled Date (Yellow) 📝 Remark/Note (Orange) – Not Entered (Grey)

## Tower 4
Tower 4 ¦ Staircase Railing ¦ Granite Fixing & MS Railing Installation
Report Date: 30 May 2026 ¦ Source: Homeland ED Tracker – Google Sheets (Live)
Floor No. | Side / Flat | Granite Fixing (GRANITE FOR STAIRCASE RAILING) | MS Railing Installation | Remarks / Notes
1 Floor | T04/11 | ✓ Done | ✓ Done
1 Floor | T04/12 | ✓ Done | ✓ Done
2 Floor | T04/21 | ✓ Done | ✓ Done
2 Floor | T04/22 | ✓ Done | ✓ Done
3 Floor | T04/31 | ✓ Done | ✓ Done
3 Floor | T04/32 | ✓ Done | ✓ Done
4 Floor | T04/41 | ✓ Done | ✓ Done
4 Floor | T04/42 | ✓ Done | ✓ Done
5 Floor | T04/51 | ✓ Done | ✓ Done
5 Floor | T04/52 | ✓ Done | ✓ Done
6 Floor | T04/61 | ✓ Done | ✓ Done
6 Floor | T04/62 | ✓ Done | ✓ Done
7 Floor | T04/71 | ✓ Done | ✓ Done
7 Floor | T04/72 | ✓ Done | ✓ Done
8 Floor | T04/81 | ✓ Done | ✓ Done
8 Floor | T04/82 | ✓ Done | ✓ Done
9 Floor | T04/91 | ✓ Done | ✓ Done
9 Floor | T04/92 | ✓ Done | ✓ Done
10 Floor | T04/101 | ✓ Done | ✓ Done
10 Floor | T04/102 | ✓ Done | ✓ Done
11 Floor | T04/111 | ✓ Done | ✓ Done
11 Floor | T04/112 | ✓ Done | ✓ Done
12 Floor | T04/121 | ✓ Done | ✓ Done
12 Floor | T04/122 | ✓ Done | ✓ Done
13 Floor | T04/131 | ✓ Done | ✓ Done
13 Floor | T04/132 | ✓ Done | ✓ Done
14 Floor | T04/141 | ✓ Done | ✓ Done
14 Floor | T04/142 | ✓ Done | ✓ Done
15 Floor | T04/151 | ✓ Done | ✓ Done
15 Floor | T04/152 | ✓ Done | ✓ Done
16 Floor | T04/161 | ✓ Done | ✓ Done
16 Floor | T04/162 | ✓ Done | ✓ Done
17 Floor | T04/171 | ✓ Done | ✓ Done
17 Floor | T04/172 | ✓ Done | ✓ Done
18 Floor | T04/181 | ✓ Done | ✓ Done
18 Floor | T04/182 | ✓ Done | ✓ Done
19 Floor | T04/191 | ✓ Done | ✓ Done
19 Floor | T04/192 | ✓ Done | ✓ Done
20 Floor | T04/201 | ✓ Done | ✓ Done
20 Floor | T04/202 | ✓ Done | ✓ Done
21 Floor | T04/211 | ✓ Done | 📝 vandor issue
21 Floor | T04/212 | ✓ Done | ✓ Done
22 Floor | T04/221 | ✓ Done | ✗ Pending
22 Floor | T04/222 | ✓ Done | ✓ Done
23 Floor | T04/231 | ✓ Done | ✗ Pending
23 Floor | T04/232 | ✓ Done | ✓ Done
24 Floor | T04/241 | ✓ Done | ✗ Pending
24 Floor | T04/242 | ✓ Done | ✗ Pending
25 Floor | T04/251 | ✗ Pending | ✗ Pending
25 Floor | T04/252 | ✗ Pending | ✗ Pending
COMPLETION SUMMARY |  | Granite Done: 48/50 = 96% | MS Railing Done: 43/50 = 86%
LEGEND: ✓ Done (Green) ✗ Pending (Red) 📅 Scheduled Date (Yellow) 📝 Remark/Note (Orange) – Not Entered (Grey)

## Tower 5
Tower 5 ¦ Staircase Railing ¦ Granite Fixing & MS Railing Installation
Report Date: 30 May 2026 ¦ Source: Homeland ED Tracker – Google Sheets (Live)
Floor No. | Side / Flat | Granite Fixing (GRANITE FOR STAIRCASE RAILING) | MS Railing Installation | Remarks / Notes
1 Floor | LHS | ✓ Done | ✓ Done
1 Floor | RHS | ✓ Done | ✓ Done
2 Floor | LHS | ✓ Done | ✓ Done
2 Floor | RHS | ✓ Done | ✓ Done
3 Floor | LHS | ✓ Done | ✓ Done
3 Floor | RHS | ✓ Done | ✓ Done
4 Floor | LHS | ✓ Done | ✓ Done
4 Floor | RHS | ✓ Done | ✓ Done
5 Floor | LHS | ✓ Done | ✓ Done
5 Floor | RHS | ✓ Done | ✓ Done
6 Floor | LHS | ✓ Done | ✓ Done
6 Floor | RHS | ✓ Done | ✓ Done
7 Floor | LHS | ✓ Done | ✓ Done
7 Floor | RHS | ✓ Done | ✓ Done
8 Floor | LHS | ✓ Done | ✓ Done
8 Floor | RHS | ✓ Done | ✓ Done
9 Floor | LHS | ✓ Done | ✓ Done
9 Floor | RHS | ✓ Done | ✓ Done
10 Floor | LHS | ✓ Done | ✓ Done
10 Floor | RHS | ✓ Done | ✓ Done
11 Floor | LHS | ✓ Done | ✓ Done
11 Floor | RHS | ✓ Done | ✓ Done
12 Floor | LHS | ✓ Done | ✓ Done
12 Floor | RHS | ✓ Done | ✓ Done
13 Floor | LHS | ✓ Done | ✓ Done
13 Floor | RHS | ✓ Done | ✓ Done
14 Floor | LHS | ✓ Done | ✓ Done
14 Floor | RHS | ✓ Done | ✓ Done
15 Floor | LHS | ✓ Done | ✓ Done
15 Floor | RHS | ✓ Done | ✓ Done
16 Floor | LHS | ✓ Done | ✓ Done
16 Floor | RHS | ✓ Done | ✓ Done
17 Floor | LHS | ✓ Done | ✓ Done
17 Floor | RHS | ✓ Done | ✓ Done
18 Floor | LHS | ✓ Done | ✓ Done
18 Floor | RHS | ✓ Done | ✓ Done
19 Floor | LHS | ✓ Done | ✓ Done
19 Floor | RHS | ✓ Done | ✓ Done
20 Floor | LHS | ✓ Done | ✓ Done
20 Floor | RHS | ✓ Done | ✓ Done
21 Floor | LHS | ✓ Done | ✓ Done
21 Floor | RHS | 📝 The lift height needs to be increased above 20. | ✗ Pending
22 Floor | LHS | ✗ Pending | ✗ Pending
22 Floor | RHS | ✗ Pending | ✗ Pending
23 Floor | LHS | ✗ Pending | ✗ Pending
23 Floor | RHS | ✗ Pending | ✗ Pending
24 Floor | LHS | - | ✗ Pending
24 Floor | RHS | - | ✗ Pending
25 Floor | LHS | - | ✗ Pending
25 Floor | RHS | - | ✗ Pending
COMPLETION SUMMARY |  | Granite Done: 41/46 = 89% | MS Railing Done: 41/50 = 82%
LEGEND: ✓ Done (Green) ✗ Pending (Red) 📅 Scheduled Date (Yellow) 📝 Remark/Note (Orange) – Not Entered (Grey)